## Slide 1: Current State of SMSE
Developing the Sharing Modelling and Simulation Environment platform

## Slide 2: Working Group on SMSE
sammy.verslype@kuleuven.be,
ludovic.espeel@kuleuven.be,
joan.peuteman@kuleuven.be,
akf1942@gmail.com,
igor_timoshchenko@yahoo.com,
Galynsky@bsu.by,
s.hvesenya@gmail.com, наверное, стоит исключить?
apldrozd@gmail.com,
dzyubenko.alan@gmail.com.
Working Group on SMSE
Thank you on feedback
More topics are upcoming

## Slide 3: What SMSE could be like?
Web-resource
Interactive Engine (probably, Jupyter Notebook)
Newsfeed
E-books materials
Course materials
JupyterHub for running online Python
nbgrader for evaluation of students
Letter is upcoming
Grading of students work
Scripts & visualization
Easier access to (some) of projects’ book
Must be discussed

## Slide 4: Free preliminary edition of SMSE
With preliminary SMSE team colleagues we will be able to work on content for SMSE early, as Google Collab is compatible with the future full version of the platform
The development of SMSE would take time → lets start creation interactive content before it is finished
Creation of Moodle section for SMSE content
Filling SMSE section on Moodle with links to Collab & related teaching notes

## Slide 5
2020
2022
"Preliminary" SMSE version
Content development
SMSE testing and implementation
Today
Dec
Feb
Apr
Jun
Aug
Oct
Dec
Feb
Apr
2020
2021
2022
17.4 days
Dec 7 - Dec 30
Development of Moodle section for placing links to Google Collaboratory and guides on interactive content
76 days
Jan 17 - May 3
Clarification and revision of the Moodle section in accordance with the requests of the project participants
203 days
Jan 5 - Oct 15
Developing interactive content on Google Collab and posting links and guides to it in a new section on Moodle
66 days
Nov 1 - Feb 1
Migration of interactive content from Moodle and Google Collab to SMSE
26 days
Dec 7 - Jan 11
Finalization of technical requirements for SMSE and E-Learning
44 days
Jan 11 - Mar 11
Preparation and holding of a tender for the development of SMSE & E-learning Platform
142 days
Apr 1 - Oct 15
Implementation of technical requirements by subcontractors and beta-testing
67 days
Nov 1 - Feb 1
Starting SMSE usage on daily basis
61 days
Jan 7 - Apr 1
Trainings, development of SMSE
SMSE working group creation
Dec 4
SMSE is developed, migration of content from Colab & Eduphys
Nov 1
Moodle section for uploading of interactive content is opened
Jan 3
Technical requirements for SMSE are finalized
Jan 3
Tender procedure is over, work begins
Apr 11
First Workshop on real SMSE prototype
Jun 20

## Slide 6: Work Package 4
Upcoming tasks:
Workshop on Google Collab before content creation starts: could please anyone make it online?
Finalization of technical requirements for SMSE is upcoming till the first week of January – letter is upcoming;
Placement of content on Moodle: a) in books’ sections; b) in separate sections.