Project 609557-EPP-1-2019-1-LV-EPPKA2-CBHE-JP “Development of practically-oriented student-centred education in the field of modelling of Cyber-Physical Systems / CybPhys of the Program ERASMUS+ EU

Workshop and Management meeting

January 12th 2021, Zoom meeting

Participated 15 representatives from 8 partners. Missed from INP BSU – due to illness; from BSU due to loss of connection (a technical problem).

Agenda:

- Information about the status

- Development and modernizing of curricula (WP2)

- Elaboration of e-books

- Other questions

  - Quality Assurance teams at the partner’ universities

- Next meeting date

Discussions and decisions

Information about the status

- The first English language lesson for team members was held on January 11th. 26 participants (22 of them are students).

- A new project team member of the Cyprus team: associate professor Irina Ciornei, Research Associate. A new list of the contact persons is available: https://eduphys.bsu.by/mod/folder/view.php?id=2248.

- Process of accreditation in Belarusian Government. From D.Marmysh by e-mail: In early December 2020, an amended application was submitted to the Government of the Republic of Belarus, taking into account all the comments made on the project. The application is currently being re-examined. The projected accreditation period is forecasted on February 2021.

- Monitoring meeting of Belarusian NEO on December 10th. Still no feedback.

- RTU – KhNAHU: discussions about Double Diploma master program are on the way. A delay is occurred due an education program of RTU, initially planned for the DD agreement, will be cancelled in 2021.

- Reminder: At the meeting in December was a decision to arrange a meeting of the WG4 on SMSE platform remotely in January.

Decision:

- To take into account the information.

- To arrange a meeting of the WG4 on SMSE platform remotely in January.

Development and modernizing of curricula (WP2). Elaboration of e-books

Participants of the meeting presented progress about both topics simultaneously.

Information about WP2 progress provided by GSU, CPTU, KhNAHU, KNU, MSPU, KU Leuven, UCY, RTU representatives. Partners presentations have been published at CybPhys home page and at e-library.

Discussion issues and decision:

- The significant progress was achieved during last two months.

- All e-books (excepted e-book 4) have co-authors from different universities and show results of collaboration between EU, Belarusian and Ukrainian universities.

- Partners presentations showed that elaboration of e-books has been delayed in comparison with initial plan.

- In order to fasten preparation of e-books it was decided to discuss progress at the meeting in February. Irina C. (UCY) offered to set a dead line after one the leaders of e-book may not wait for materials from co-authors, but they have to finalise existing content of e-books.

- Partners presentation about WP2 will be attached (including info from BSU) to the Minutes.

- Anatolijs Z. (RTU) offered that Belarusian and Ukrainian teem leaders (D.Marmysh and V.Kazymyr) will update the tables of new/ modernized courses at e-library.

Quality Assurance teams at the partner’ universities

Stella H. (UCY) reminded the partners about nomination of members of internal Quality teams.

Discussion issues and decision:

- In order to avoid a conflict of interest recommendations to the partners will be prepared (Stella)

Project communication

Stella H. (UCY) asked partners to pay attention to CybPhys Facebook group, since too few participant and visits are noticed. New members are needed!

Anatolijs Z. asked Belarusian partners to consider opportunity of creation a CybPhys group in any social network, which is popular in Belarus, e.g. VKontakte, etc.

A.K. Fedotov asked (it was sent later by e-mail) to remind that none of the project participants (excepted KU Leuven) sent him the Communication Report supplemented for July-December, although at the last meeting it was reminded.

Further tasks and the next steps

Irina C. (UCY) offered to discuss teachers and students training. The topic and suggestions of UCY team will be discussed at the meeting in February.

The next meeting at Zoom platform:

The next Management Zoom meeting will be held on February 8th, Monday, 15.00 (Latvian time), with an agenda:

- Elaboration of e-books WP2.

- Teachers and students training arrangement.

It is offered a schedule for next CybPhys meetings:

- February 8th Monday

- March 1st Monday

Project Coordinator:                                                     Anatolijs Zabašta, RTU