Project 609557-EPP-1-2019-1-LV-EPPKA2-CBHE-JP “Development of practically-oriented student-centred education in the field of modelling of Cyber-Physical Systems / CybPhys of the Program ERASMUS+ EU

Workshop and Management meeting

February 8th 2021, Zoom meeting

18 representatives from all 10 partners participated at the meeting.

Agenda:

- Information about the status

- Development and modernizing of curricula (WP2)

- Teachers and students training arrangement

- Other questions

  - Quality Assurance teams at the partner’ universities

  - Dissemination issues

- Next meeting date

Discussions and decisions

Information about the status

- WP4: A meeting of the WP4 working group was arranged on February 3rd. 18 persons took part in the WS.

  - One can find documents related this working group at https://eduphys.bsu.by/course/view.php?id=84#section-9

  - The next meeting of this WG will be held on Wednesday of February 17.

- The updated list of the contact persons is available on “Partners agreements”: https://eduphys.bsu.by/mod/folder/view.php?id=2248 .

- Process of accreditation in Belarusian Government is still ongoing. BSU does not have information about its status.

- RTU – KhNAHU: discussions about Double Diploma master program are on the way.

Decision:

- To take into account the information.

- BSU colleagues will try to find out the status of accreditation of CybPhys in Belarusian Government.

Development and modernizing of curricula (WP2). Elaboration of e-books

Information about WP2 progress was presented by colleagues from UCY, KU Leuven, BSU, GSU, CPTU, KhNAHU, KNU, MSPU, RTU representatives.

The partners demonstrated progress in the development of e-books.

Discussion issues and decision:

- The significant progress was achieved during last month. The e-book 6 is approaching to the finish.

- In order to fasten preparation of e-books it was decided to discuss progress at the meeting in March.

- Partners promised to send missed chapters to the e-books leaders.

Teachers and students training arrangement

I. Ciornei presented teachers training plan. EU partners achieved a preliminary commitment to arrange a single training one-week event at the end of August or beginning of September 2021. The event will be held at the premises of UCY. All EU partners will contribute to the training.

- Option A (probable): full on line

- Option B (highly probable): hybrid format (some participants to be physically present on premises of the UCY, others on line).

- Option C (ideal case): physical presence.

Discussion issues and decision:

- To accept the plan offered by Irina.

- To start preparation according to the plan.

Quality Assurance teams at the partner’ universities

Stella H. (UCY) presented the list of members of internal Quality teams and answered to the partner’s questions.

Project communication

A.K. Fedotov reminded to the partners to send him the monthly Dissemination reports.

A.Zabašta asked partners to send monthly at least one material, which can be published at CybPhys homepage for the project visibility. J.Peuteman describe examples of such dissemination materials.

Decision:

To take into account this information and suggestions.

The next meeting at Zoom platform:

The next Management Zoom meeting will be held on March 1st, Monday, 15.00 (Riga and Nicosia time), with an agenda:

- Development and modernizing of curricula (WP2). Progress of e-books.

- Development of SMSE platform. Information from WP4 working group.

It is offered a schedule for next CybPhys meetings:

- March 1st, Monday

- April 5th, Monday

Project Coordinator:                                                     Anatolijs Zabašta, RTU